## Sheet1
Author | Douglas Bahr
Date | 2016-10-18
Project | DDS Tone shield
Bring Up Change List
Version | Engineer | Issue | Resolution | Documentation Updated
REV 1 | Douglas Bahr | POT 5k pads are off | Repad Pot and replace it on board
REV 1 | Douglas Bahr | POT 100k Pads are off | Repad Pot and replace it on board
REV 1 | Douglas Bahr | DIP SWITCH pad package is wrong | Figure out where the issue cropped up to note how to avoid it in the future before changing the package size and replaceing the part
REV 1 | Douglas Bahr | Change placement of Via under ON/ON Switch to not be under switch to stop issue of placement of part | Rewire the via
REV 1 | Douglas Bahr | Anular ring size is too small on all pads /vias | Altium resize the pads/vias
REV 1 | Douglas Bahr | VIA drill size not complient with 22 guage wire | Change Sizes in altium
REV 1 | Douglas Bahr | DDS Filter design layout is messy | Replace pads and retrace the lines
REV 1 | Douglas Bahr | DDS filter change pad/part sizes for easier reworking | Replace pads or modify pads after placement
REV 1 | Douglas Bahr | Board outline trace exists | Figure out problem and remove it
REV 1 | Douglas Bahr | Resister/led is in wrong order | Switch in sketch then replace in document
REV 1 | Douglas Bahr | Sketch is wrong with connection to VCC POT 100k | Change part library and update schematic
REV 1 | Douglas Bahr | Layout is wrong with connection to VCC POT 100k | Replace and retrace part in layout
REV 1 | Douglas Bahr | No test points/hard to debug | Add test points and other connections directly to board layout