## Sheet1
Tasks: | SubTask: | Subber Tasks | Subberer Tasks: | Min: |  |  | Hours | Actual Time
Meta Time task List:
| Making a time task list for time task list |  |  | 3 |  |  |  | 3
| Making a time list for other parts of projects |  |  | 90 |  |  |  | 90
| Review |  |  | 15 |  |  |  | 20
| Bring up |  |  | 25
| Bring up v2.0 |  |  | 15
[5 empty] | 148 | :Total | 2.4667
Architecture | [9 empty] | Time Management Software
| Testing Definitions | [9 empty] | Research | 20
|  | Talk With Malcolm |  | 15 | [6 empty] | Find | 10
|  | Thinking about Definitions |  | 15 | [6 empty] | Download | 20
|  | Writing it out |  | 60 | [6 empty] | learn | 15
|  | Editing |  | 10 | [6 empty] | evaluate | 10
|  | Submitting and feeling good about myself |  | 5 | [6 empty] | Cycle x2 | 50
|  | Hating myself and reedditing |  | 20 | [6 empty] | TOTAL | 125
|  | Finalize |  | 5 | [5 empty] | Setup Templates
[5 empty] | 130 | :Total | 2.1667 |  |  |  | Evaluate EA templates | 15
Realization | [10 empty] | Define new task: Learning | 10
| Adding Changed DRC rules altium | [9 empty] | Capture Sleep cycle work info | 5
|  | Figuring out how to output custom rules |  | 20 | [6 empty] | Create Single Template | 90
|  | Export the rules |  | 5 | [6 empty] | Create template folder structure | 10
|  | Reimport and evaluate |  | 10 | [6 empty] | TOTAL | 130
|  | Submit |  | 1 | [5 empty] | Email Emma
| Adding BOM altium | [9 empty] | Write up email | 20
|  | Figuring out altium |  | 25 | [5 empty] | Call Malcolm
|  | Bomb for each part | [9 empty] | 60
|  |  | Each Part 10 min average. 16 + part | 160
|  | Outputting bomb |  | 5
|  | Figuring out why outputing doesn't work |  | 45
|  | Output bomb |  | 2 | [5 empty] | Study Art
|  | Figure out why one specific thing of it doesn’t work |  | 55 | [5 empty] | Read
|  | Outputting bomb |  | 2 | [5 empty] | Program
|  | Format for submit |  | 5 | [6 empty] | TOTAL | 590
Cable Definitions
|  | Talk With Malcolm |  | 5
|  | Formating sheet |  | 15
|  | Submitting |  | 5
Command List
|  | Talk with Malcom |  | 15
|  | Review Examples |  | 10
|  | Create template |  | 25
|  | Edit |  | 5
|  | Submit |  | 2
[5 empty] | 417 | :Total | 6.95
Fabrication
Assemble
|  | Solder components to board |  | 90
|  | Verify line trace connections |  | 25
|  | Fix any Structrual issues |  | 45
[5 empty] | 160 | :Total | 2.6667
Coding
Validate DDS attiny85
Take Sketch Program and load it into attiny85
|  |  | Setup Circuit for testing | 20
|  |  | Set up attiny85 bootloader | 10
|  |  | Load it on | 2
|  |  | Test | 5
|  |  | Figure out why test didn't work | 15
|  |  | A few more cycles of loading and unloading with minor changes | 45
|  |  | Test | 10
Valide subrutines for on/on
|  | Code |  | 20
|  | Use Arduino to test values of off/on for baseline |  | 15
|  | validate test with state indicator light |  | 10
|  | recode |  | 5
|  | validate |  | 25
Valide subrutines for Manual frequency
|  | Code |  | 60
|  | Use Arduino to test values for baseline |  | 15
|  | Write code to change frequency based on input |  | 25
|  | Validate change with arduino/test |  | 15
|  | Debug and recode |  | 25
|  | Test |  | 15
|  | Import into attiny |  | 35
|  | validate test |  | 25
Validate Library arduino communicates with Attiny85
|  | Come up with cumminication Guideline |  | 30
Program Arduino to output guidelines
|  |  | Code arduino | 25
|  |  | Run test | 15
|  |  | Repeat | 40
Verify with another arduino that the output guidelines are outputted
|  |  | Code Arduino | 15
|  |  | Setup Test | 20
|  |  | Run test | 15
|  |  | Repeat | 35
|  | Convert Arduino reciever into attiny code |  | 35
|  | set up test to verify that cumminication works |  | 45
|  | Test that communication works |  | 10
|  | Bring up |  | 25
|  | Verify again |  | 15
| Integration |  |  |  | 540 | 9
|  | Try to take different parts and put them into same Body |  | 120
|  | Set up tests |  | 25
|  | Debug and recode |  | 90
|  | test again and verrify output |  | 25
|  | Debug and recode |  | 30
|  | Verify test |  | 25
|  | Optimize |  | 30
|  | Test |  | 10
|  | Figure out huge error |  | 80
|  | final compile |  | 30
[5 empty] | 1187 | :Total | 19.7833
Bring Up
Bring up change list
Round 1
|  |  | Structural problems including foot/part placement issues | 45
|  |  | Line issues | 35
|  |  | Part Place Issues | 25 |  |  |  |  | Malcolm Note
|  |  | Increase Pad size and retrace | 25 |  |  |  |  | Each Feature spend time to bring up each feature that is located in the feature block diagram
|  |  | Add in test points/line connections for testing | 20 |  |  |  |  | I'm going to spend certain amount of time to bring up each feature.
|  |  | Rework board to make it testable | 25
|  |  | Try driving parts of the board to test functionality | 35
|  |  | Modify board for arduino testing | 20
|  |  | Reorder parts for new board | 25
Round 2
|  |  | new board | 45
|  |  | Desolder/resolder parts onto new board | 50
|  |  | Verify connections between all points | 25
|  |  | Try driving parts with board/arduino to test functionality | 90
|  |  | Figure out how to fix problem (Probably DDS) | 120
|  |  | Figure out other issues | 90
|  |  | Bring up | 60
Round 3
|  | *MIGHT NOT BE NECESSARY* | new board | 45
|  | *MIGHT NOT BE NECESSARY* | Desolder/resolder parts onto new board | 50
|  |  | Verify connections between all points | 25
|  |  | Try driving parts with board/arduino to test functionality | 25
|  |  | Figure out other issues | 30
Rework Tracking
|  | Board 1 | Write out rework | 35
|  | Board 2 | Write out rework | 25
|  | Board 3 | Write out rework | 25
|  | Board 4 | Write out rework | 25
[5 empty] | 1020 | :Total | 17
Testing
| Data Acquisition | Round 1
|  |  | Setup Sound Test chamber | 45
|  |  | Setup Sound Test Enviroment computer | 90
|  |  | Run Test | 25
|  |  | Figure out errors | 25
|  |  | Run Test | 30
Round 2
|  |  | Setup Test | 15
|  |  | Run Tests | 10
|  |  | Verify test | 10
|  |  | Figure out bringup | 15
|  |  | Next test stage of product testing | 45
Round 3
|  |  | Setup remaining tests | 90
|  |  | Run tests | 300
|  |  | Data acquisition | 15
|  |  | Run tests | 150
|  |  | Data acquisition | 15
Testing Change List
Round 1
|  |  | Analyze data | 25
|  |  | Figure out solution to issue | 90
|  |  | Apply solution | 25
Round 2
|  |  | Analyze data | 25
|  |  | Figure out remaining problems | 30
|  |  | apply soluton | 15
round 3
|  |  | Anayze data | 45
|  |  | Generate meaningful graphs | 90
|  |  | Figure out what to do: Malcolm | 15
Final Release |  |  |  |  | 1240 | :TOTAL | 20.6667
[7 empty] | 69.2333 | :SUM TOTAL
1